## Slide 1: Georgia Gateway – Training & Implementation Update
Tony McGaughey, Sonia Jackson, Susan Wall & Sid Peecharagadi
NSD Meeting
March 28-29, 2017

## Slide 2: Overview
Updates on the Georgia Gateway WIC program
Training Implementation Schedule
Progress of Henry County Pilot Implementation
Upcoming Events
Comments, Suggestions and Feedback

## Slide 3: Objectives
Develop a training schedule with flexibility for Gateway Implementation
Compile ideas regarding Georgia WIC Gateway Implementation from the pilot District’s perspective
Identify productivity requirements and reporting

## Slide 4: Progress of Henry County Pilot Implementation

## Slide 5: Progress of Henry County Pilot Implementation
Preparedness
Began communication with clients three (3) months prior to Pilot
Posted communication on District 4-0 WIC Facebook page
Reduced certification schedule
Weekly Gateway conference calls with State Office
Challenges
System challenges (User roles, Driver flow, Webcenter Enabled Capturing (WEC) scanning, Document Imaging System (DIS)
Conversion (Clients unable to be processed)
WIC Policies vs. Gateway Business Rules
Notes: Susan: Go into more detail about conversion user roles, etc.
Susan: Discuss changes between policies and gateway business rules

## Slide 6: Progress of Henry County Pilot Implementation (cont.)
Lessons Learned
Communication is key
Keep regular appointment schedules - set daily % goal of certifications done in Gateway
Include case number on WIC folder (create labels)
Recognize staff’s hard work/morale boosters
Impact on Work Force
Additional responsibilities for clerical staff
Notes: Susan: Incorporate pictures

## Slide 7: Training implementation

## Slide 8: Training Implementation
To ease the training burden on the districts:
Implementation Options
  Staggered district rollout
  Entire district rollout
  Reduced certification schedule

## Slide 9: Rollout Completion Dates
Wave 1
  50% = May 19, 2017
  75% = June 2, 2017
  100% = June 16, 2017
Wave 2a
  50% = July 21, 2017
  75% = August 4, 2017
  100% = August 18, 2017
Wave 2b (NEW) – Fulton, DeKalb & Gwinnett
  To be determined (TBD)

## Slide 10: Potential Scenarios
Notes: Talk out the scenarios and provide as many visuals as possible to the learner, if possible.

## Slide 11
Clinic 1
Clinic 2
Clinic 3
Clinic 4
Wk 1 Wk 2 Wk 3 Wk 4 Wk 5 Wk 6 Wk 7 Wk 8 Wk 9
20% 30% 40% 45% 55% 70% 80% 90% 100%
30% 45% 55% 70% 75% 85% 95% 100% 100%
40% 60% 75% 85% 95% 100% 100% 100% 100%
20% 35% 45% 50% 65% 75% 85% 90% 95%
15% 25% 40% 55% 65% 70% 80% 85% 90%
Clinic 5
% % % % % % % % %
Notes: We will use this as a visual for the potential scenarios so that we can talk about how the districts can have clinics at varying levels of implementation.

## Slide 12: Management of Productivity
Reporting
  Voucher Management And Reporting System (VMARS) Dashboard
  Comparison of Gateway applications vs. total certifications completed in front-end systems
  Weekly
    District submission to Program Operation Specialists
    Spreadsheet
Notes: Tony: Share spreadsheet and VMARS dashboard

## Slide 13: Train-the-Trainer Updates
WIC Only (Train-the-Trainer) Training Sessions will be four (4) days long
Wave 1 Training
  April 4-7, 2017
  April 17-20, 2017
Wave 2a Training
  April 25-28, 2017 (held in Macon)
  May 15-18, 2017 (held in Augusta)
  May 22-25, 2017 (TBD)
  June 6-9, 2017 (held in Dublin)
Wave 2b Training
  TBD
Notes: We are working with the southern districts to get a training location in early June.

## Slide 14: District Training Schedule
Staff training for Wave 1 must be completed by May 12, 2017
Staff training for Wave 2 must be completed by June 16, 2017

## Slide 15: Additional Training Options to Consider
Trainers will conduct teach back sessions:
  One trainer will pose as a trainer
  Other trainer will pose as a classroom assistant
  Trainers will switch after one week
Note: State Office Staff will be available to supplement district training staff in the event of an approved emergency
Notes: Trainer: Train material as if you are training to a class.
Classroom Assistant: Over the shoulder support for the trainees
Tony: Staff can decide how they would like to group who will train and who will be a classroom assistant

## Slide 16: District Training Locations
Each district must submit their locations to complete staff trainings

## Slide 17: Next Steps for Training & Implementation
Nutrition Services Directors shall do the following:
  Work with WIC-Gateway Project Manager to develop district training schedules
  Submit training/implementation schedule which includes:
    Date of training
    Location of training
    Staff to be trained at each location
    Gateway Training and Implementation Scheduling Form
All staff shall do the following:
  Register through the State
  Complete the web based training (Learning Management System)
  Attend the four (4) day classroom training

## Slide 18: Gateway Training and Implementation Scheduling Form

## Slide 19: Gateway Training and Implementation Scheduling Form (cont.)

## Slide 20: Gateway Training and Implementation Scheduling Form (cont.)

## Slide 21: Gateway Training and Implementation Scheduling Form (cont.)

## Slide 22: Gateway Training and Implementation Scheduling Form (cont.)

## Slide 23: Next Steps for Training and Implementation (cont.)
Districts shall submit training schedules
  To Sid Peecharagadi and Sonia Jackson
  By April 7, 2017
Complete and submit Gateway Security & Confidentiality Form
  To Barry Cross
  By April 7, 2017
Notes: Sonia: Reference Gateway Security & Confidentiality Form

## Slide 24: Summary
Finalizing the following:
  Training sites
  District training schedules
  Secure SOG logins for staff
  Ensure all staff have completed web based training

## Slide 25
Sonia Jackson
Program Review and Delivery Manager
WIC Program – Operations Unit
Georgia Department of Public Health
2 Peachtree Street, NW, 10th Floor
Atlanta, Georgia 30303
Phone: 404-657-2908
Email Address: Sonia.Jackson@dph.ga.gov
Susan E. Wall
Nutrition Services Director, Health District 4
301 Main Street,
LaGrange, Georgia 30240
Mobile: 706-298-6097
Email Address: Susan.Wall@dph.ga.gov
Tony McGaughey
Systems & Applications Director Office of Information Technology Georgia Department of Public Health
2 Peachtree Street, NW (12-428) Atlanta, GA 30303 404.657.3105 Office
Email Address: Anthony.McGaughey@dph.ga.gov
Sid Peecharagadi PMP®
Sr. Project Manager – GA Gateway WIC
Georgia Department of Public Health
2 Peachtree St NE (10-405)
Atlanta, GA 30303
Mobile: 404 408 8644
Email Address: Sid.Peecharagadi@dph.ga.gov
Notes: Talking point: Sid is the main contact for all questions about Gateway; will divert questions accordingly

## Slide 26: What questions do you have?